*SEDAR 48 Southeastern Black Grouper (Benchmark)*

Data Deadline: ???

RW: March 2017 (tentative) – St. Petersburg, FL

Terminal Year of Data: 2015

Report Available to Council: April 2017

Coordinator: Julie

*SEDAR 50 – SA Blueline Tilefish (Benchmark)*

Stock ID Work Group Meeting:June 28-30, 2016

Ageing Workshop: August 29-31, 2016

Life History Data Deadline: 1 November 2016

Landings Data Deadline: 3 January 2017

DW: January 23-27, 2017 – Charleston

AW: May 23-26, 2017 - TBD

Assessment webinars: March-July 2017

RW: August 22-24, 2017 - TBD

Terminal Year of Data: 2015

Report Available to Council: September 2017

Coordinator: Julia

*SEDAR 51 – Gulf of Mexico Gray Snapper (Benchmark)*

Gray Snapper Stock ID Webinars – November 2016 (tentative)

Raw Life History and Length Comp Data Deadline: 30 January 2017

Landings Data Deadline: 3 April 2017

DW: April 24-28, 2017 - Tampa/St. Pete (tentative)

Assessment webinars: June – September 2017

RW: November 14-16, 2017 – Miami, FL

Terminal Year of Data: 2015

Report Available to Council: April 2018

Coordinator: Julie

SEDAR 52 – *Gulf of Mexico Red Snapper (Standard)*

Data Deadline: 1 August 2017

In-person workshop: November 29- December 1, 2017– Miami, FL

Terminal Year of Data: 2016

Report Available to Council: March 2018

Coordinator: Julie

SEDAR 53 –*SA Red Grouper (Standard)*

Data Deadline: 5 September 2016

Assessment webinars: November 2016 – January 2017

Terminal Year of Data: 2015

Report Available to Council: February 2017

Coordinator: Julie

SEDAR 54 – *HMS Sandbar Shark (Standard)*

Data Deadline: 7 April 2017

Assessment Webinars: May-August 2017

Terminal Year of Data: 2015

Report Available to Cooperator: January 2018

Coordinator: Julie

Other Assessments/data needs scheduled for 2017:

Update for SA Vermilion Snapper:

Data Deadlines: 30 June 2017 (landings); 18 September 2017 (other data sets)

Terminal Year of Data: 2016

Report Available to Council: April 2018

Coordinator: Julia

Update for HMS Blacktip Shark:

Data Deadline: 15 September 2017

Terminal Year of Data: 2016

Report Available to Cooperator: April 2018

Coordinator: Julie

MRIP Catch Revisions – South Atlantic:

Species:

Data Deadline:

Terminal Year of Data: 2016

Report Available to Council: April 2018

Coordinator: Julia

MRIP Catch Revisions – Gulf of Mexico:

Species:

Data Deadline:

Terminal Year of Data: 2016

Report Available to Council: April 2018

Coordinator: Julie

Stock ID and Meristics Procedural Workshop

Location: Atlanta

*Data Deadlines Summary Table (arranged in chronological order by data deadline)*

|  |  |  |
| --- | --- | --- |
| **SEDAR Project** | **Data Deadline** | **Assessment Approach** |
| SEDAR 50 – Atlantic blueline tilefish | 3 January 2017 (Landings) | Benchmark |
| SEDAR 51 – GoM gray snapper | 30 January 2017 (Raw Life History and Length Comps) | Benchmark |
| SEDAR 51 – GoM gray snapper | 3 April 2017 (Landings) | Benchmark |
| SEDAR 54 – HMS sandbar shark | 7 April 2017 | Standard |
| SA vermilion snapper | 30 June 2017 (Landings) | Update |
| SEDAR 52 – GoM red snapper | 1 August 2017 | Standard |
| HMS Gulf Blacktip Shark | 15 September 2017 | Update |
| SA vermilion snapper | 18 September 2017 (All other data sets) | Update |